## Latest Version
Phase-wise | No. | Description | Description | Status | Remark | Total Resource Required | Resources | Priority | Timeline in Days | APS Estimates in man days | APS comments
Phase 1 | 1 | Page setup is not available need to adjust manually | In Page setup we can adjust the page size A4, Letter, A5 and custom sizes including top,bottom, left and right margins, background colors, watermarks | Not Available |  | 2 | 0.5 - Team Lead 0.5 - Tester 1 - Web Developer
Phase 1 | 2 | Flow layout and other layouts are not available | Flow layout and other includes newspaper layout format | Not Available | Sample required | 2 | 0.5 - Team Lead 0.5 - Tester 1 - Web Developer
Phase 1 | 3 | Font size | Font size in points and need to know which font we need to refer like px,% and pt is not available | font size is available everywhere | PT -points in size not available | 2 | 0.5 - Team Lead 0.5 - Tester 1 - Web Developer
Phase 1 | 4 | Header and Footer placement as per A4 or custom page | Custom pagewise header and footer placements | Not Available |  | 2 | 0.5 - Team Lead 0.5 - Tester 1 - Web Developer
Phase 1 | 5 | Page break | Add new page | Not Available |  | 2 | 0.5 - Team Lead 0.5 - Tester 1 - Web Developer
Phase 1 | 6 | Placement issues | Controls placement issues in layout |  |  | 2 | 0.5 - Team Lead 0.5 - Tester 1 - Web Developer
Phase 1 | 7 | Drawing control | Not available | Not Available |  | 2 | 0.5 - Team Lead 0.5 - Tester 1 - Web Developer
Phase 1 | 8 | Textbox not available | Not available with borders | Textbox is available | With Borders is required | 2 | 0.5 - Team Lead 0.5 - Tester 1 - Web Developer
Phase 1 | 9 | Export to PDF is not accurate | The quality of o/p documents is not correct or appropriate | Not Accurate |  | 2 | 0.5 - Team Lead 0.5 - Tester 1 - Web Developer
Phase 1 | 10 | Transaction table | Dynamic data growing table |  | Sample required | 2 | 0.5 - Team Lead 0.5 - Tester 2 - Web Developer |  |  |  | The table content should display the complete rows and columns based on the json table. Currently the content is captured as screenshot in PDF wherein the table shown incomplete data.
Phase 1 | 11 | Show/hide | Conditional show/hide elements | Not Accurate |  | 2 | 0.5 - Team Lead 0.5 - Tester 1 - Web Developer
Phase 1 | 12 | Highlight | Conditional highlighting of text | Not Available |  | 1 | 0.5 - Team Lead 0.5 - Tester 1 - Web Developer
Phase 1 | 13 | Everytime new or need to replace the .html file (Not Required) | (Not Required) |  |  | 2 | 0.5 - Team Lead 0.5 - Tester 1 - Web Developer
Phase 1 | 14 | Formatting | Margin, border, header, currency, to be shown footer to be shown options Formatting is seen not as par designer like borders, pageno,date,number formatting costmetics and etc |  |  | 2 | 0.5 - Team Lead 0.5 - Tester 1 - Web Developer
Phase 1 | 15 | Dynamic | Dynamic data logics/conditional data logic, show hide contents, image etc | Not Available |  | 2 | 0.5 - Team Lead 0.5 - Tester 1 - Web Developer
Phase 1 | 16 | Bar code | All bar code required [ incl 2D Barcode and as per industry standards ] | Not Available |  | 2 | 0.5 - Team Lead 0.5 - Tester 1 - Web Developer
Phase 1 | 17 | QR code | Not available | Not Available |  | 1.5 | 0.5 - Team Lead 0.5 - Tester 1 - Web Developer
Phase 1 | 18 | Page number | Not available | Not Available |  | 2 | 0.5 - Team Lead 0.5 - Tester 1 - Web Developer
Phase 1 | 19 | Need to update Chart properties | Not done require jason |  |  | 2 | 0.5 - Team Lead 0.5 - Tester 1 - Web Developer
Phase 1 | 20 | Dynamic page header,footer and content | Pagewise dynamic header, footer and content not available | Not Available |  | 2 | 0.5 - Team Lead 0.5 - Tester 1 - Web Developer
Phase 1 | 21 | Complexity seen in simple static template development | Due to limitation this not as flexible as per static designer tool |  |  | 2 | 0.5 - Team Lead 0.5 - Tester 1 - Web Developer
Phase 1 | 22 | Hyperlink | Target within the page | Not Available |  | 2 | 0.5 - Team Lead 0.5 - Tester 1 - Web Developer
Phase 1 | 23 | Table of content | Navigate within the page | Not Available |  | 2 | 0.5 - Team Lead 0.5 - Tester 1 - Web Developer
Phase 1 | 24 | Multi- Jason feature need to implement | Single & multiple both option should be available |  |  | 2 | 0.5 - Team Lead 0.5 - Tester 1 - Web Developer
Phase 1 | 25 | Quality of output document (Considered item no.9) |  | NOT REQUIRED |  | 2 | 0.5 - Team Lead 0.5 - Tester 1 - Web Developer
Phase 1 | 26 | Marque to add |  |  |  | 2 | 0.5 - Team Lead 0.5 - Tester 1 - Web Developer
Phase 1 | 27 | Separator to add |  |  |  | 2 | 0.5 - Team Lead 0.5 - Tester 1 - Web Developer
Phase 1 | 28 | Scripting is required | Java scripting To show hide contents, images, table etc |  |  | 2 | 0.5 - Team Lead 0.5 - Tester 1 - Web Developer
Phase 1 | 29 | FrontEnd for Api is Required - List of all the saved templates with edit, view, delete options - view and edit option will open in the Interactive designer tool with that selected template - API1(single json to single html) - select template option and select single json option and submit. It should download html with selected json data - API2(multiple json to multiple html) - select json folder, select template, select output folder and submit -Error handling and logs option of every things. |  |  |  | 2 | 0.5 - Team Lead 0.5 - Tester 1 - Web Developer
Phase 1 | 30 | Page Option - First screen should be list of pages - add new page - Once select the new page it should open interactive tool - To add a new page again ,option on page button and than add new page so that 2 or more pages can be created - Pages should be like add new page button and if the created page is already exist than url, edit, delete button should be available - url button shouls give us a ID/url so that it can be given in navbar or button or on some text redirect url - Edit button in an interactive tool of that selected page to edit - Delete button to delete a selected page - Options to download or save in pdf format or in html format (it will give a proper layout one below another) | Creating new Page(multipages) |  |  | 2 | 0.5 - Team Lead 0.5 - Tester 1 - Web Developer
Phase 1 | 31 | Error and logs for API not received | This already covered in point no 31 |  |  | 2 | 0.5 - Team Lead 0.5 - Tester 1 - Web Developer
Phase 1 | 32 | API UI for generating PDF Static PDF Bulk and Realtime | API UI is required for static PDF generation via Bulk and Realtime | Not Available |  | 2 | 0.5 - Team Lead 0.5 - Tester 1 - Web Developer
Phase 1 | 33 | Download final output with additional option for PDF | Download/Generate PDF directly from interactive designer instead of generating from HTML | Not Available |  | 2 | 0.5 - Team Lead 0.5 - Tester 1 - Web Developer
Phase 1 | 34 | Page format | Landscape/portrait [horizonal/veritical] | Not Available |  | 2 | 0.5 - Team Lead 0.5 - Tester 1 - Web Developer
Phase 2 | 35 | Password Protection in tool for PDF | Password to open PDF | Not Available |  | 2 | 0.5 - Team Lead 0.5 - Tester 1 - Web Developer
Phase 1 | 36 | Page selection | Which page should be in the download version | Not Available |  | 2 | 0.5 - Team Lead 0.5 - Tester 1 - Web Developer
Phase 1 | 37 | Text Rotation |  | Not Available |  | 2 | 0.5 - Team Lead 0.5 - Tester 1 - Web Developer
Phase 1 | 38 | Conditional Page break | Events on page break | Not Available |  | 2 | 0.5 - Team Lead 0.5 - Tester 1 - Web Developer
Phase 2 | 39 | Hide on Prints(conditional) |  | Not Available |  | 2 | 0.5 - Team Lead 0.5 - Tester 1 - Web Developer
Phase 1 | 40 | Running Total | A running total or rolling total is the summation of a sequence of numbers which is updated each time a new number is added to the sequence, by adding the value of the new number to the previous running total. | Not Available |  | 2 | 0.5 - Team Lead 0.5 - Tester 1 - Web Developer
Phase 2 | 41 | Chart | Chart json data should editable for Legends and tooltip | Interactive - Improvement |  | 2 | 0.5 - Team Lead 0.5 - Tester 1 - Web Developer
Phase 1 | 42 | Read only View | Read only View for radio button, bullet point, checkbox, select choices, date picker combo etc. | Not Available |  | 2 | 0.5 - Team Lead 0.5 - Tester 1 - Web Developer
Phase 1 | 43 | Form - select | it should do something after selecting. For eg. Account numbers are showing in the select ten after selecting that account number that json tag/array should be showing the data below | Interactive |  | 2 | 0.5 - Team Lead 0.5 - Tester 1 - Web Developer
Phase 1 | 44 | Text json connect | In a single textbox at some word we can give a json tag. For eg. "This Interactive statement is showcasing data of {01-07-2024 to 31-07-2024}. It is not showing current day details." in between {} its is from json tag. | Interactive - Improvement |  | 2 | 0.5 - Team Lead 0.5 - Tester 1 - Web Developer
Phase 1 | 45 | After saving the template/design Design view and o/p View is not matching | After saving the template/design the desgin should not change a bit -Alignment | Interactive - Improvement |  | 2 | 0.5 - Team Lead 0.5 - Tester 1 - Web Developer
Phase 2 | 46 | carousel | carousel is doent work proper need to ease | Interactive - Improvement |  | 2 | 0.5 - Team Lead 0.5 - Tester 1 - Web Developer
Phase 1 | 47 | Tabs | Tabs first tab should be active | Interactive - Improvement |  | 2 | 0.5 - Team Lead 0.5 - Tester 1 - Web Developer
Phase 2 | 48 | Music in the background | playing background music while viewing interactive statement i. control will be provided to associate/upload mp3, .wav file ii. checkbox to run it in loop. | Interactive - Improvement |  | 2 | 0.5 - Team Lead 0.5 - Tester 1 - Web Developer
Phase 2 | 49 | Read Out Loud |  | Not Available |  | 2 | 0.5 - Team Lead 0.5 - Tester 1 - Web Developer
Phase 1 | 50 | Grouping and Summary | Categorization data (sorting)with view for multiple accounts | Not Available |  | 2 | 0.5 - Team Lead 0.5 - Tester 1 - Web Developer
Phase 1 | 51 | Formula | Customized formula | Not Available |  | 2 | 0.5 - Team Lead 0.5 - Tester 1 - Web Developer
Phase 2 | 52 | Cross Tabs |  | Not Available |  | 2 | 0.5 - Team Lead 0.5 - Tester 1 - Web Developer
Phase 1 | 53 | Designer Console Screen | To display Error & handling messages | Not Available |  | 2 | 0.5 - Team Lead 0.5 - Tester 1 - Web Developer
Phase 1 | 54 | Table | a)Table json content proper heading getting merge (bug) b) Customization/Editing table's property with customized styles c) Alignment of Columns in the table | Interactive - Improvement |  | 2 | 0.5 - Team Lead 0.5 - Tester 1 - Web Developer
Phase 1 | 55 | Background Image (static/Dynamic) | Background image can be static or dynamic and watermark option not available | Not Available |  | 2 | 0.5 - Team Lead 0.5 - Tester 1 - Web Developer
Phase 1 | 56 | Subreport | Parent and child report linking | Not Available |  | 2 | 0.5 - Team Lead 0.5 - Tester 1 - Web Developer
Phase 2 | 57 | Required outputs txt,csv, docs,rtf & xls, Postscript(PS) Output | Printing purpose | Not Available |  | 2 | 0.5 - Team Lead 0.5 - Tester 1 - Web Developer
Phase 1 | 58 | Parameter | Require parameter for preview | Not Available |  | 2 | 0.5 - Team Lead 0.5 - Tester 1 - Web Developer
Phase 2 | 59 | Sheet break | Similar to page break | Not Available |  | 2 | 0.5 - Team Lead 0.5 - Tester 1 - Web Developer
Phase 1 | 60 | Section | Require section to place the control and for free-hand development | Not Available |  | 2 | 0.5 - Team Lead 0.5 - Tester 1 - Web Developer
Phase 1 | 61 | Report Explorer | To view the placement of elements | Not Available |  | 2 | 0.5 - Team Lead 0.5 - Tester 1 - Web Developer
Phase 2 | 62 | Separate Datasource option for PDF view |  | Not Available |  | 2 | 0.5 - Team Lead 0.5 - Tester 1 - Web Developer
Phase 1 | 63 | Password Protection in tool for HTML | Navigating in design pages using json password logic | Not Available |  | 2 | 0.5 - Team Lead 0.5 - Tester 1 - Web Developer
Phase 1 | 64 | Multilingual | Multilingual in the Output | Not Available |  | 2 | 0.5 - Team Lead 0.5 - Tester 1 - Web Developer
Phase 2 | 65 | ListBox, mutiselect | Up and down on attributes like arrow button |  |  | 2 | 0.5 - Team Lead 0.5 - Tester 1 - Web Developer
Phase 1 | 66 | Code Encryption, Code Minification ,Code Obfuscation is required | Encryption with AES 256 algorithm |  |  | 2 | 0.5 - Team Lead 0.5 - Tester 1 - Web Developer
Phase 1 | 67 | Designer should be platform independent | Designer should work and deploy on all OS like Windows, Linux, Mac, solaris etc |  |  | 2 | 0.5 - Team Lead 0.5 - Tester 1 - Web Developer
0
0

## Sheet1
12 | 4
10 | 6
4 | 10
14 | 4
12 | 8
6 | 8
12 | 6
4 | 10
10 | 4
0 | 12
4 | 6
5
0
6
12
10
7.5
4
0
0
12
6
14
20
0
8
6
12
25
20
4
8
6
2
4
1
6
8
4
8
4
2
6
8
6
10
4
4
16
8
7
20
4
16
16
10
447.5 | 78 | 525.5

## Latest Version (2)
Phase-wise | No. | Description | Description | Remark | ATS Remark | Priority | Resources | Timeline in Days |  | Total Resource Required | APS Estimates in man days | APS comments | Status
Phase 1 | 1 | Page setup is not available need to adjust manually | In Page setup we can adjust the page size A4, Letter, A5 and custom sizes including top,bottom, left and right margins, background colors, watermarks |  | clear | high | 0.5 - Team Lead 0.5 - Tester 1 - Web Developer | 1 | canvas size, like A4, letter, margin, watermark | 2 |  |  | Not Available
Phase 1 | 2 | Flow layout and other layouts are not available | Flow layout and other includes newspaper layout format | Sample required | not clear | Low (need clarity | 0.5 - Team Lead 0.5 - Tester 1 - Web Developer | 2 | need to ask sir and client | 2 |  |  | Not Available
Phase 1 | 3 | Font size | Font size in points and need to know which font we need to refer like px,% and pt is not available | PT -points in size not available | clear | high | 0.5 - Team Lead 0.5 - Tester 1 - Web Developer | 1 | need to display default size with unit, need to add PT as well | 2 |  |  | font size is available everywhere
Phase 1 | 4 | Header and Footer placement as per A4 or custom page | Custom pagewise header and footer placements |  | clear | high | 0.5 - Team Lead 0.5 - Tester 1 - Web Developer | 1 | for particular page identify fefault header & footer. default there on page, option to remove or resize in page setup. | 2 |  |  | Not Available
Phase 1 | 5 | Page break | Add new page |  | clear | medium | 0.5 - Team Lead 0.5 - Tester 1 - Web Developer | 1 | same like word new page option. add new page option in page setup | 2 |  |  | Not Available
Phase 1 | 6 | Placement issues | Controls placement issues in layout |  | need to test | Low | 0.5 - Team Lead 0.5 - Tester 1 - Web Developer | 1 |  | 2
Phase 1 | 7 | Drawing control | Not available |  | clear | high | 0.5 - Team Lead 0.5 - Tester 1 - Web Developer | 2 | paint controls | 2 |  |  | Not Available
Phase 1 | 8 | Textbox not available | Not available with borders | With Borders is required | available | high | 0.5 - Team Lead 0.5 - Tester 1 - Web Developer | 1 | already implimented under decorations option | 2 |  |  | Textbox is available
Phase 1 | 9 | Export to PDF is not accurate | The quality of o/p documents is not correct or appropriate |  | clear | high | 0.5 - Team Lead 0.5 - Tester 1 - Web Developer | 1 | capturing using html2canvas as a Screenshot, need to convert using text to pdf or using jspdf | 2 |  |  | Not Accurate
Phase 1 | 10 | Transaction table | Dynamic data growing table | Sample required | need to test | medium | 0.5 - Team Lead 0.5 - Tester 2 - Web Developer | 1 | need to test by using table data | 2 |  | The table content should display the complete rows and columns based on the json table. Currently the content is captured as screenshot in PDF wherein the table shown incomplete data.
Phase 1 | 11 | Show/hide | Conditional show/hide elements |  | clear | low | 0.5 - Team Lead 0.5 - Tester 1 - Web Developer | 1 | same as point 15 | 2 |  |  | Not Accurate
Phase 1 | 12 | Highlight | Conditional highlighting of text |  | clear | high | 0.5 - Team Lead 0.5 - Tester 1 - Web Developer | 1 |  | 1 |  |  | Not Available
Phase 1 | 13 | Everytime new or need to replace the .html file (Not Required) | (Not Required) |  | not clear |  | 0.5 - Team Lead 0.5 - Tester 1 - Web Developer |  |  | 2
Phase 1 | 14 | Formatting | Margin, border, header, currency, to be shown footer to be shown options Formatting is seen not as par designer like borders, pageno,date,number formatting costmetics and etc |  | clear | low | 0.5 - Team Lead 0.5 - Tester 1 - Web Developer | 1 | new option in page setup date/time stamp and currency | 2
Phase 1 | 15 | Dynamic | Dynamic data logics/conditional data logic, show hide contents, image etc |  | clear | low | 0.5 - Team Lead 0.5 - Tester 1 - Web Developer | 1 | on json data or simple string match. Hide complete page or that particular word | 2 |  |  | Not Available
Phase 1 | 16 | Bar code | All bar code required [ incl 2D Barcode and as per industry standards ] |  | clear | medium | 0.5 - Team Lead 0.5 - Tester 1 - Web Developer | 2 | need to add barcode generator feature | 2 |  |  | Not Available
Phase 1 | 17 | QR code | Not available |  | clear | medium | 0.5 - Team Lead 0.5 - Tester 1 - Web Developer | 2 | QR code generator in settings | 1.5 |  |  | Not Available
Phase 1 | 18 | Page number | Not available |  | clear | medium | 0.5 - Team Lead 0.5 - Tester 1 - Web Developer | 1 | want to display page numbers in the PDF file as well as on canvas | 2 |  |  | Not Available
Phase 1 | 19 | Need to update Chart properties | Not done require jason |  | clear | medium | 0.5 - Team Lead 0.5 - Tester 1 - Web Developer | 5 |  | 2
Phase 1 | 20 | Dynamic page header,footer and content | Pagewise dynamic header, footer and content not available |  | clear | high | 0.5 - Team Lead 0.5 - Tester 1 - Web Developer | 1 | already covered in point 4 | 2 |  |  | Not Available
Phase 1 | 21 | Complexity seen in simple static template development | Due to limitation this not as flexible as per static designer tool |  | clear | low | 0.5 - Team Lead 0.5 - Tester 1 - Web Developer | 2 | ( where is complexity? ) want to ask in meetings | 2
Phase 1 | 22 | Hyperlink | Target within the page |  | clear | high | 0.5 - Team Lead 0.5 - Tester 1 - Web Developer | 2 | addition of link in index, will jump directly on that content | 2 |  |  | Not Available
Phase 1 | 23 | Table of content | Navigate within the page |  | clear | medium | 0.5 - Team Lead 0.5 - Tester 1 - Web Developer | 2 | same as hyperlink | 2 |  |  | Not Available
Phase 1 | 24 | Multi- Jason feature need to implement | Single & multiple both option should be available |  | clear | high | 0.5 - Team Lead 0.5 - Tester 1 - Web Developer | 2 | same as like single json | 2
Phase 1 | 25 | Quality of output document (Considered item no.9) |  |  |  |  | 0.5 - Team Lead 0.5 - Tester 1 - Web Developer |  |  | 2 |  |  | NOT REQUIRED
Phase 1 | 26 | Marque to add |  |  | clear | medium | 0.5 - Team Lead 0.5 - Tester 1 - Web Developer | 2 | html marque tags | 2
Phase 1 | 27 | Separator to add |  |  | clear | high | 0.5 - Team Lead 0.5 - Tester 1 - Web Developer | 2 | new component for separator like line separator, donnted, bold separator etc | 2
Phase 1 | 28 | Scripting is required | Java scripting To show hide contents, images, table etc |  | available | high | 0.5 - Team Lead 0.5 - Tester 1 - Web Developer | 1 |  | 2
Phase 1 | 29 | FrontEnd for Api is Required - List of all the saved templates with edit, view, delete options - view and edit option will open in the Interactive designer tool with that selected template - API1(single json to single html) - select template option and select single json option and submit. It should download html with selected json data - API2(multiple json to multiple html) - select json folder, select template, select output folder and submit -Error handling and logs option of every things. |  |  | clear | low | 0.5 - Team Lead 0.5 - Tester 1 - Web Developer | 2 | ( which external API we are using? ) | 2
Phase 1 | 30 | Page Option - First screen should be list of pages - add new page - Once select the new page it should open interactive tool - To add a new page again ,option on page button and than add new page so that 2 or more pages can be created - Pages should be like add new page button and if the created page is already exist than url, edit, delete button should be available - url button shouls give us a ID/url so that it can be given in navbar or button or on some text redirect url - Edit button in an interactive tool of that selected page to edit - Delete button to delete a selected page - Options to download or save in pdf format or in html format (it will give a proper layout one below another) | Creating new Page(multipages) |  | clear | medium | 0.5 - Team Lead 0.5 - Tester 1 - Web Developer | 4 |  | 2
Phase 1 | 31 | Error and logs for API not received | This already covered in point no 31 |  | clear | medium | 0.5 - Team Lead 0.5 - Tester 1 - Web Developer | 1 | in java while developing API covered in point 31 | 2
Phase 1 | 32 | API UI for generating PDF Static PDF Bulk and Realtime | API UI is required for static PDF generation via Bulk and Realtime |  | clear |  | 0.5 - Team Lead 0.5 - Tester 1 - Web Developer | 2 | add option to display saved templates and drag, drop in canvas | 2 |  |  | Not Available
Phase 1 | 33 | Download final output with additional option for PDF | Download/Generate PDF directly from interactive designer instead of generating from HTML |  | available | high | 0.5 - Team Lead 0.5 - Tester 1 - Web Developer | 1 | already implimented | 2 |  |  | Not Available
Phase 1 | 34 | Page format | Landscape/portrait [horizonal/veritical] |  | clear | high | 0.5 - Team Lead 0.5 - Tester 1 - Web Developer | 1 | coverd in point 1, option of page format | 2 |  |  | Not Available
Phase 2 | 35 | Password Protection in tool for PDF | Password to open PDF |  | clear | high | 0.5 - Team Lead 0.5 - Tester 1 - Web Developer | 1 | user will manually select checkbox and will add passward for protection. Provide password format | 2 |  |  | Not Available
Phase 1 | 36 | Page selection | Which page should be in the download version |  | clear | high | 0.5 - Team Lead 0.5 - Tester 1 - Web Developer | 1 | check custom platform independent pdf download tool | 2 |  |  | Not Available
Phase 1 | 37 | Text Rotation |  |  | available | high | 0.5 - Team Lead 0.5 - Tester 1 - Web Developer | 1 | option is available in extra using transform feature | 2 |  |  | Not Available
Phase 1 | 38 | Conditional Page break | Events on page break |  | clear | low | 0.5 - Team Lead 0.5 - Tester 1 - Web Developer | 1 | need to ask | 2 |  |  | Not Available
Phase 2 | 39 | Hide on Prints(conditional) |  |  | clear | low | 0.5 - Team Lead 0.5 - Tester 1 - Web Developer | 1 | while downloading will condition like odd/even/custom | 2 |  |  | Not Available
Phase 1 | 40 | Running Total | A running total or rolling total is the summation of a sequence of numbers which is updated each time a new number is added to the sequence, by adding the value of the new number to the previous running total. |  | clear | medium | 0.5 - Team Lead 0.5 - Tester 1 - Web Developer | 1 | total running addition like crystal report | 2 |  |  | Not Available
Phase 2 | 41 | Chart | Chart json data should editable for Legends and tooltip |  | clear | medium | 0.5 - Team Lead 0.5 - Tester 1 - Web Developer | 2 | covered in point 19 | 2 |  |  | Interactive - Improvement
Phase 1 | 42 | Read only View | Read only View for radio button, bullet point, checkbox, select choices, date picker combo etc. |  | available | high | 0.5 - Team Lead 0.5 - Tester 1 - Web Developer | 1 | option for pdf preview, for canvas view option is already there in EYE button | 2 |  |  | Not Available
Phase 1 | 43 | Form - select | it should do something after selecting. For eg. Account numbers are showing in the select ten after selecting that account number that json tag/array should be showing the data below |  | clear | low | 0.5 - Team Lead 0.5 - Tester 1 - Web Developer | 2 | dependent dropdown | 2 |  |  | Interactive
Phase 1 | 44 | Text json connect | In a single textbox at some word we can give a json tag. For eg. "This Interactive statement is showcasing data of {01-07-2024 to 31-07-2024}. It is not showing current day details." in between {} its is from json tag. |  | clear | high | 0.5 - Team Lead 0.5 - Tester 1 - Web Developer | 1 | after adding json text previously added keyboard text is dissapearing | 2 |  |  | Interactive - Improvement
Phase 1 | 45 | After saving the template/design Design view and o/p View is not matching | After saving the template/design the desgin should not change a bit -Alignment |  | need to test | high | 0.5 - Team Lead 0.5 - Tester 1 - Web Developer | 1 | ( alrady covered in point 9 ) | 2 |  |  | Interactive - Improvement
Phase 2 | 46 | carousel | carousel is doent work proper need to ease |  | need to test | low | 0.5 - Team Lead 0.5 - Tester 1 - Web Developer | 2 | need to check what is carousel and its features | 2 |  |  | Interactive - Improvement
Phase 1 | 47 | Tabs | Tabs first tab should be active |  | available | low | 0.5 - Team Lead 0.5 - Tester 1 - Web Developer | 1 | in extra section tab component for drag and drop is available | 2 |  |  | Interactive - Improvement
Phase 2 | 48 | Music in the background | playing background music while viewing interactive statement i. control will be provided to associate/upload mp3, .wav file ii. checkbox to run it in loop. |  | clear | high | 0.5 - Team Lead 0.5 - Tester 1 - Web Developer | 1 | add option to add background music same as background animataion | 2 |  |  | Interactive - Improvement
Phase 2 | 49 | Read Out Loud |  |  | clear | medium | 0.5 - Team Lead 0.5 - Tester 1 - Web Developer | 1 | need to check for readymade feature | 2 |  |  | Not Available
Phase 1 | 50 | Grouping and Summary | Categorization data (sorting)with view for multiple accounts |  | clear | low | 0.5 - Team Lead 0.5 - Tester 1 - Web Developer | 1 | readymade datatable grouping | 2 |  |  | Not Available
Phase 1 | 51 | Formula | Customized formula |  | clear | medium | 0.5 - Team Lead 0.5 - Tester 1 - Web Developer | 2 | new component for formula same like word | 2 |  |  | Not Available
Phase 2 | 52 | Cross Tabs |  |  | not clear | low | 0.5 - Team Lead 0.5 - Tester 1 - Web Developer | 3 | need to check crystal report cross tab function | 2 |  |  | Not Available
Phase 1 | 53 | Designer Console Screen | To display Error & handling messages |  | clear | low | 0.5 - Team Lead 0.5 - Tester 1 - Web Developer | 1 | need to develop own console | 2 |  |  | Not Available
Phase 1 | 54 | Table | a)Table json content proper heading getting merge (bug) b) Customization/Editing table's property with customized styles c) Alignment of Columns in the table |  | clear | medium | 0.5 - Team Lead 0.5 - Tester 1 - Web Developer | 1 | solve minor issues in table component | 2 |  |  | Interactive - Improvement
Phase 1 | 55 | Background Image (static/Dynamic) | Background image can be static or dynamic and watermark option not available |  | clear | medium | 0.5 - Team Lead 0.5 - Tester 1 - Web Developer | 1 | make separate component watermark. for watermark provide option of text and image | 2 |  |  | Not Available
Phase 1 | 56 | Subreport | Parent and child report linking |  | clear | low | 0.5 - Team Lead 0.5 - Tester 1 - Web Developer | 2 | want to check how it is generating | 2 |  |  | Not Available
Phase 2 | 57 | Required outputs txt,csv, docs,rtf & xls, Postscript(PS) Output | Printing purpose |  | not clear | low | 0.5 - Team Lead 0.5 - Tester 1 - Web Developer | 2 | need to ask client what you want in postscript | 2 |  |  | Not Available
Phase 1 | 58 | Parameter | Require parameter for preview |  | clear | high | 0.5 - Team Lead 0.5 - Tester 1 - Web Developer | 1 | print option | 2 |  |  | Not Available
Phase 2 | 59 | Sheet break | Similar to page break |  | clear | high | 0.5 - Team Lead 0.5 - Tester 1 - Web Developer | 1 | automatic | 2 |  |  | Not Available
Phase 1 | 60 | Section | Require section to place the control and for free-hand development |  | clear | low | 0.5 - Team Lead 0.5 - Tester 1 - Web Developer | 5 | move elements using mouse | 2 |  |  | Not Available
Phase 1 | 61 | Report Explorer | To view the placement of elements |  | clear | low | 0.5 - Team Lead 0.5 - Tester 1 - Web Developer | 2 | check crystal report | 2 |  |  | Not Available
Phase 2 | 62 | Separate Datasource option for PDF view |  |  | not clear | low | 0.5 - Team Lead 0.5 - Tester 1 - Web Developer | 2 | need to clear from client | 2 |  |  | Not Available
Phase 1 | 63 | Password Protection in tool for HTML | Navigating in design pages using json password logic |  | clear | low | 0.5 - Team Lead 0.5 - Tester 1 - Web Developer | 1 | user will add condition, like | 2 |  |  | Not Available
Phase 1 | 64 | Multilingual | Multilingual in the Output |  | clear | low | 0.5 - Team Lead 0.5 - Tester 1 - Web Developer | 1 | Already Implimented in HTML/ZIP | 2 |  |  | Not Available
Phase 2 | 65 | ListBox, mutiselect | Up and down on attributes like arrow button |  | clear | high | 0.5 - Team Lead 0.5 - Tester 1 - Web Developer | 1 | using keyboard aroow keys or need to add arrow keys in canvas? | 2
Phase 1 | 66 | Code Encryption, Code Minification ,Code Obfuscation is required | Encryption with AES 256 algorithm |  | clear | medium | 0.5 - Team Lead 0.5 - Tester 1 - Web Developer | 3 | will add checkbox of enpryption while downloading zip. while downloading zip it will display option of want encryption ? | 2
Phase 1 | 67 | Designer should be platform independent | Designer should work and deploy on all OS like Windows, Linux, Mac, solaris etc |  | clear | low | 0.5 - Team Lead 0.5 - Tester 1 - Web Developer | 1 |  | 2
[8 empty] | 100 |  | 0
0

## Sheet2
Phase 1 | 2 | Flow layout and other layouts are not available | Flow layout and other includes newspaper layout format | Sample required | not clear | need to ask sir and client | The Flow Layout and Newspaper Layout options are already available under the Basic section in the "+" (Add) icon menu. Please let us know if you are expecting any additional features or specific enhancements to these layouts in upcoming updates.
Phase 1 | 6 | Placement issues | Controls placement issues in layout |  | need to test |  | Could you kindly specify: Which control placement issues you are referring to within the layout? - Are there particular controls that are not aligning correctly or behaving unexpectedly? - Also, please let us know if you're expecting any new control types to be added to the layout toolbox. This will help us address your concerns precisely.
Phase 1 | 21 | Complexity seen in simple static template development | Due to limitation this not as flexible as per static designer tool |  | clear | ( where is complexity? ) want to ask in meetings | Could you please elaborate on where you are noticing complexity during the development of simple static templates? - Are there specific features or design tools that are not user-friendly? - Understanding this will help us improve the overall workflow and simplify the experience for end users.
Phase 2 | 46 | carousel | carousel is doent work proper need to ease |  | need to test | need to check what is carousel and its features | The Carousel feature is already implemented in the Interactive Designer and is functioning as expected based on the original requirements. Could you please specify any issues, bugs, or user experience concerns you’re facing? That will help us identify and resolve them effectively, if needed.
Phase 2 | 62 | Separate Datasource option for PDF view |  |  | not clear | need to clear from client | We'd appreciate some clarification regarding this point. Are you requesting the ability to use a different datasource specifically for PDF export, separate from the one used during on-screen design/preview? If yes, we can implement a system where: - The editor uses test or sample data, and - The final export pulls data from a separate production datasource. Please confirm if this interpretation is correct or provide additional details.
Phase 2 | 57 | Required outputs txt,csv, docs,rtf & xls, Postscript (PS) Output | Printing purpose |  | not clear | need to ask client what you want in postscript | Please note that formats like TXT, CSV, RTF, and XLS are primarily intended for text and tabular data. Images, videos, and GIFs cannot be exported into these formats in their original form. - For such media, we can include descriptive placeholders or filenames where appropriate. - Let us know if you'd like to include such placeholders for reference in these exported files.