## Sheet1
Task No. | Task | Description as per scope (Excel) sheet | ATS understanding of task | Iteration 1 Feedback | Iteration 2 Feedback | Iteration 3 Feedback | Status
1 | Parameter | Require parameter for preview | Instead of directly downloading the PDF, the system first shows how the PDF will look. This allows users to open a preview window and review the layout and content before choosing to download the final PDF. | A preview option to show data coming from JSON before it appears in the editor. This helps display only the required part of data for review instead of loading everything into the editor and export into PDF as well as in HTML. |  |  | Completed with Demo
2 | Read only View | Read only View for radio button, bullet point, checkbox, select choices, date picker combo etc. | A feature of Read Only View in the editor to check the working of radio buttons, checkboxes, and selection choices before exporting. | No Feedback |  |  | Completed with Demo
3 | Password Protection in tool for PDF | Password to open PDF | An option to set a password for the PDF before downloading it. Once the PDF is downloaded, it will require the entered password to open. | Custom password protection for PDFs generated using JSON data. The password can be created from one or more data fields during PDF generation. | It should ask the file location while downloading |  | Completed with Demo
4 | Export to PDF is not accurate | The quality of o/p documents is not correct or appropriate | The quality of the exported PDF was improved. Earlier, when zooming in, the content used to get blurred. Now, the exported text remains clear and can also be selected. | No Feedback |  |  | Completed with Demo
5 | Textbox not available | Not available with borders | Borders to text box elements for better layout design. | No Feedback |  |  | Completed with Demo
6 | Font size | Font size in points and need to know which font we need to refer like px,% and pt is not available | Font size selection in points (pt). | No Feedback |  |  | Completed with Demo
7 | Separator to add | Not Available | A separating line element was added so that users can place it wherever needed in the document. | No Feedback |  |  | Completed with Demo
8 | Page Option - First screen should be list of pages - add new page - Once select the new page it should open interactive tool - To add a new page again ,option on page button and than add new page so that 2 or more pages can be created - Pages should be like add new page button and if the created page is already exist than url, edit, delete button should be available - url button shouls give us a ID/url so that it can be given in navbar or button or on some text redirect url - Edit button in an interactive tool of that selected page to edit - Delete button to delete a selected page - Options to download or save in pdf format or in html format (it will give a proper layout one below another) | Creating new Page(multipages) | A page management feature is added where the first screen displays a list of all created pages along with an "Add New Page" option. -When a user clicks "Add New Page", it opens the interactive designer tool to design the new page. -To add more pages, users can again click the page button and select "Add New Page", allowing the creation of two or more pages. -Edit – opens the selected page in the interactive designer tool for editing. Delete – removes the selected page from the system. Users can download or save all created pages together in either PDF format or HTML format, arranged properly one below another. | No Feedback |  |  | Completed with Demo
9 | Page break | Add new page | Page break element so that elements move to the next page if available, If page is not available then it will create a new page and moves content on new page. This will happen only while exporting to pdf | Page break element so that elements move to the next page if available, If page is not available then it will create a new page and moves content on new page. This wil happen in editor also |  |  | Completed with Demo
10 | Page number | Not available | Customizable page numbering with options for placement, text color, borders, and predefined styles. | Page no. rotation is required |  |  | Feedback demo pending
11 | Page setup is not available need to adjust manually | In Page setup we can adjust the page size A4, Letter, A5 and custom sizes including top, bottom, left and right margins, background colors, watermarks | Page setup options were required. These includes page size, margins, orientation, background color, watermark. | Include tiled watermark option for Text and Image type watermark. |  |  | Completed with Demo
12 | Hide on Prints(conditional) | Not Described in Scope Document | Each element now has an option to remain visible in the editor but stay hidden when exporting to PDF via selecting checkbox through settings. | No Feedback |  |  | Completed with Demo
13 | Header and Footer placement as per A4 or custom page | Custom pagewise header and footer placements | Custom headers and footers can be set for each page. Users can adjust their height, add content, and select which pages should have them. | No Feedback |  |  | Completed with Demo
14 | Formatting | Margin, border, header, currency, to be shown footer to be shown options Formatting is seen not as par designer like borders, pageno, date, number formatting costmetics and etc | Formatting options for text elements were added. Numbers, dates, currency, and percentages can be formatted in different international styles. | Required indonesian and Oman specific currency and format. | Additional country-specific currency formats were required and added as per feedback. |  | Completed with Demo
15 | Dynamic page header, footer and content | Pagewise dynamic header, footer and content not available | A Separate Drag and Drop Element having Header, content, footer. | Dynamic headers and footers were required. Different pages can now have different headers and footers, and the data for these can be taken from JSON dynamically. Options like Odd pages, Even pages, Odd and Even pages, Custom Range added. | Options like First page only, Last page only, First and Last page required. |  | Feedback WIP
16 | Formula | Customized formula | Formula support for table required. | Formulas can be used not only in tables but also in text boxes. | The formulas like Add, Sub, Avg, Mean, Absolute, Max, Min, Round up, Percentage, NumberToWords also required to the existing formula list if not available. |  | Completed with Demo
17 | Need to update Chart properties | Not done require jason | All chart types requested by the client (provided in Document) were required. Earlier, only limited charts were available. | No Feedback |  |  | Completed with Demo
18 | Complexity seen in simple static template development | Due to limitation this not as flexible as per static designer tool | Elements can now be resized using the mouse directly, instead of adjusting their size only through settings. | No Feedback |  |  | Completed with Demo
19 | Hyperlink | Target within the page | Hyperlinks required in the document or HTML so they work after export. Internal page navigation was added. | Feedback, if a link points to the same page, it will be disabled automatically In exported document. |  |  | Completed with Demo
20 | Table of content | Navigate within the page | A table of contents (TOC) element were required. The text from the header is used to generate the TOC. The TOC lists the content sections and links them for navigation. | To generate TOC aspecial Header element Required. In header element data can be come from JSON. | A header element upto 7 level with Custom styling and custom spacing in levels for the TOC was also required. |  | Completed with Demo
21 | Marque to add | Not Described in Scope Document | A marquee tag feature was required, which allows text or content to scroll as per the requirements. | No Feedback |  |  | Completed with Demo
22 | Show/hide | Conditional show/hide elements | Text boxes can now show or hide data based on a set text or numeric condition. | No Feedback |  |  | Completed with Demo
23 | Dynamic | Dynamic data logics/conditional data logic, show hide contents, image etc | A feature was required to show or hide data dynamically using scripts. This works for both manually added data and data coming from JSON. | No Feedback |  |  | Completed with Demo
24 | Download final output with additional option for PDF | Download/Generate PDF directly from interactive designer instead of generating from HTML | PDF generation was changed. Earlier it generated PDFs as images; now it generates them as text, so the content remains text-based with additional options of page layout, orientation change, addition of margin, changing scale. | Single page option required, All data present on editor will come in single page of PDF after Export | Extra space at bottom observed in downloaded PDF |  | Feedback demo pending
25 | Drawing control | Not available | Drawing controls such as predefined shapes, pencil, eraser, etc, etc were required. Users can draw freely. | Separate elements for line, circle, and rectangle also required. |  |  | Completed with Demo
26 | Background Image (static/Dynamic) | Background image can be static or dynamic and watermark option not available | Background image or watermark options were required. Both text and image watermarks can be used. | A tiled option want for text watermark and for image watermark. |  |  | Completed with Demo
27 | Music in the background | playing background music while viewing interactive statement i. control will be provided to associate/upload mp3, .wav file ii. checkbox to run it in loop. | A music element was required using an audio component with mp3, .wav file. | Checkbox to play in loop. | A single icon to control sound instead of a full audio player. |  | Completed with Demo
28 | Read Out Loud | Not Described in Scope Document | The feature used the operating system’s narrator and some browser built-in options to read PDF and HTML exports aloud. | Now needs to be update to use Text-to-Speech (TTS) for proper read-out-loud functionality in HTML. | APS will test about voice modulation, region wise tone |  | Completed with Demo
29 | Section | Require section to place the control and for free-hand development | A section element was required where each section has its own header, content, and footer. Element free hand development is required in that. | Each of these can be customized for all pages, even pages, odd pages, or custom selections. There is also an option to print the footer at the bottom. For JSON data, each row will appear on a separate page, and content will be filled continuously. |  |  | Feedback demo pending
30 | Bar code | All bar code required [ incl 2D Barcode and as per industry standards ] | Industry-standard barcodes and 2D barcodes were required, and the barcode type can be customized. | No Feedback |  |  | Completed with Demo
31 | QR code | Not available | A QR code generation feature was required. | No Feedback |  |  | Completed with Demo
32 | Highlight | Conditional highlighting of text | Conditional highlighting for text was required.Based on Conditions such as text cointains, Number greater than, less than, equal to, not equal to, etc conditional highlighting will work. | Include highlighting in tables (both local and JSON data tables) and null values check condition. | Condition selection from a dropdown. | To handle single condition, multiple conditions, and One off condition for highlighting, change font size | Completed with Demo
33 | Scripting is required | Java scripting To show hide contents, images, table etc | JavaScript scripting was required to allow showing or hiding data, content, images, and tables. | No Feedback |  |  | Completed with Demo
34 | Placement issues | Controls placement issues in layout | Elements inside section areas can now be freely moved and resized using the mouse, instead of making these changes only through settings. | No Feedback |  |  | Completed with Demo
35 | API UI for generating PDF Static PDF Bulk and Realtime | API UI is required for static PDF generation via Bulk and Realtime | A user interface for real-time bulk PDF generation using JSON data and designed templates is required. | It should ask the file location while downloading |  |  | Completed with Demo
36 | Page format | Landscape/portrait [horizonal/veritical] | Options to set pages as landscape or portrait during initial setup were required. | No Feedback |  |  | Completed with Demo
37 | Chart | Chart json data should editable for Legends and tooltip | Editable legends and tooltips for charts. | Customization of legend display and position |  |  | Completed with Demo
38 | Running Total | A running total or rolling total is the summation of a sequence of numbers which is updated each time a new number is added to the sequence, by adding the value of the new number to the previous running total. | This feature calculates a cumulative sum of numbers and updates it automatically when new records or transactions are added. |  |  |  | Feedback demo pending
39 | Grouping and Summary | Categorization data (sorting)with view for multiple accounts | Add a feature to group records, sort them within groups, and see totals or subtotals. It should also allow viewing data from many accounts together and then open each account to see details. | Need to add merge group cell option |  |  | Feedback demo pending
40 | Table | a)Table json content proper heading getting merge (bug) b) Customization/Editing table's property with customized styles c) Alignment of Columns in the table | Make JSON table data editable and easy to style. The headings should not merge, and users should be able to change column alignment. |  |  |  | Completed with Demo
41 | Subreport | Parent and child report linking | A link between parent and child reports. The main report (parent) can include one or more detailed reports (child). They should be linked so users can open detailed data from the main summary in HTML export | able to pass parameter from main report to subreport |  |  | Feedback demo pending
42 | Sheet break | Similar to page break | A feature similar to a page break to divide content into pages. | flow layout same review/ APS will be discussing it internally on this point |  |  | Completed with demo
43 | Multilingual | Multilingual in the Output | After exporting to HTML, add an option to change language. Available languages are Marathi, Hindi, English, and Tamil. | No Feedback |  |  | Completed with Demo
44 | Conditional Page break | Events on page break | A conditional page break that checks rules to decide when to add a new page. | Condition on every page independently | for more dynamic need to share script |  | Feedback demo 2 pending
45 | Form - select | It should do something after selecting. For eg. Account numbers are showing in the select ten after selecting that account number that json tag/array should be showing the data below | When adding a table from JSON, an option is provided to filter the data first so that only the selected data is imported into the editor. The filtered data can then be exported to PDF or HTML. | ATS to share script |  |  | Completed with Demo
46 | Text json connect | In a single textbox at some word we can give a json tag. For eg. "This Interactive statement is showcasing data of {01-07-2024 to 31-07-2024}. It is not showing current day details." in between {} its is from json tag. | Allow placing JSON tags inside a text field. These tags will be replaced with real data from JSON when exporting. |  |  |  | Completed with Demo
47 | carousel | carousel is doent work proper need to ease | Keep carousel elements fixed in the place where they are added. They should not move to the end automatically. | No Feedback |  |  | Completed with Demo
48 | FrontEnd for Api is Required | FrontEnd for Api is Required - List of all the saved templates with edit, view, delete options - view and edit option will open in the Interactive designer tool with that selected template - API1(single json to single html) - select template option and select single json option and submit. It should download html with selected json data - API2(multiple json to multiple html) - select json folder, select template, select output folder and submit -Error handling and logs option of every things. | Create a front-end screen to manage APIs with the interactive designer. It should: • Show all saved templates with view, edit, and delete options. • Open selected templates directly in the designer. • Have two APIs: one to create a single HTML file from one JSON and one to create many HTML files using multiple JSON files. • Show errors, logs, and status for each process. | To edit template, template will open in same tab only. On clicking option "New Template" Interactive designer screen will open in new tab. |  |  | Completed with Demo
49 | Error and logs for API not received |  | Add proper error handling and logs for all API processes. | 1. Add pagination 2. Filter on results 3. Export in excel 4. Name of template edited and deleted in log details |  |  | Completed with Demo
50 | Report Explorer | To view the placement of elements | Add a Report Explorer panel that shows all elements in a tree view. Users can quickly find and select elements without searching manually | Show element ID in tree view |  |  | Completed with Demo
51 | After saving the template/design Design view and o/p View is not matching | After saving the template/design the desgin should not change a bit -Alignment | Save templates with the exact same alignment so when used again, the layout does not change. |  |  |  | Completed with Demo
52 | Cross Tabs |  | Add a feature to create a matrix or pivot-style table. This table will show summarized values where rows and columns meet. | Table structure should be editable | APS will share demo pdf |  | Feedback demo pending
53 | Required outputs txt,csv, docs,rtf & xls, Postscript(PS) Output | Printing purpose | Add export options so reports can be downloaded as TXT, CSV, DOC/RTF, XLS/XLSX, and also as PostScript (PS) for printing. |  |  |  | Completed with Demo
54 | ListBox, mutiselect | Up and down on attributes like arrow button |  |  |  |  | Completed with Demo
55 | Text Rotation | Not Described in Scope Document | An option to rotate text box. |  |  |  | Completed with Demo
56 | Separate Datasource option for PDF view | Not Described in Scope Document |  | XML datasource should be acceptable |  |  | Completed with Demo
57 | Password Protection in tool for HTML |  | Password protection for HTML export, similar to PDF password protection. |  |  |  | Completed with Demo
58 | Flow layout and other layouts are not available | Flow layout and other includes newspaper layout format | Fix flow layout so text wraps properly like in a newspaper layout. | obsevations in table and multiple columns. |  |  | Feedback demo pending
59 | Code Encryption, Code Minification ,Code Obfuscation is required | Encryption with AES 256 algorithm | An option to encrypt HTML exports using AES 256 when enabled. |  |  |  | Completed & Demo pending
60 | Page selection | Which page should be in the download version | A feature to select which pages to include in print or PDF. |  |  |  | Completed with Demo
61 | Transaction table | Dynamic data growing table | A table that grows automatically when new data is added. It should handle real-time updates and large data without manual setup. | Bug: Extra row populating | export pdf demo pending |  | Feedback demo 2 pending
62 | Tabs | Tabs first tab should be active | A tab layout where multiple content sections are under different tabs. The first tab should open by default. This is for HTML. | No Feedback |  |  | Completed with Demo
63 | Designer Console Screen | To display Error & handling messages | Provides a dedicated panel within the interactive designer to display errors, warnings. | Bug: Recent logs were not displaying |  |  | Feedback demo pending
64 | Designer should be platform independent | Designer should work and deploy on all OS like Windows, Linux, Mac, solaris etc | Make the interactive designer work on all operating systems like Windows, Linux, Mac, and Solaris. |  |  |  | Completed
65 | Multi- Jason feature need to implement | Single & multiple both option should be available | Add an option to upload and use multiple JSON files at the same time. |  |  |  | Completed with Demo